# Velaivaaipu Job Portal — Enhancement Plan

Compressed delivery: all 7 items scoped to land inside a 6–8 calendar-day window.

Repo: CT_Jobportal (client + server) · Stack: React 19 / Vite, Node / Express 5, MongoDB · Date: 2026-09-15

How this fits 6–8 days. The original estimate for full scope was 34–51 developer-days. To land in 6–8 calendar days, this revision does two things: (1) splits the work into 3 developers running in parallel tracks instead of one, and (2) narrows each item to its essential fix, deferring the larger builds — document-upload verification, preference centers, full analytics overhauls — to a Phase 2 backlog. One developer cannot deliver full scope in 6–8 days

# Scope at a Glance

| Item | Kept in this window | Deferred to Phase 2 | Effort |
| --- | --- | --- | --- |
| Email notifications | Coverage audit; add 2–3 highest-value missing triggers; smoke-test in staging | User preference center, digest batching, retry/alerting infrastructure | 1 days |
| Payment gateway | Functional QA pass in test mode: checkout, webhook simulation, refund, signature check | Invoice/receipt polish, retry & dunning UX | 1 days |
| Dashboard | Resolve duplicate jobseeker dashboard; add 1–2 priority charts | Full analytics overhaul, admin platform-wide dashboard, widget rollout to every role | 1 days |
| Verification, in detail | Consistent status badges, rejection reason + resubmission path, lightweight audit-trail log on existing approve/reject actions | New document-upload + review workflow (est. 3–4 additional days on its own) | 1.5 days |
| Job inventory / messages | Fix unwired search box in Messages.jsx; regression test | — fully resolved in this window | 1 day |
| Profile update | Fix role→endpoint routing bug (company/Settings.jsx ↔ recruiter route gate); regression test all 5 roles | — fully resolved in this window | 1 day |
| Notifications | Coverage audit; add missing in-app triggers; smoke test | Dedicated notification history page, preference center | 1.5 days |

# Parallel Delivery Schedule

Track A — Critical Fixes, Email, Notifications

Day 1  Reproduce and fix the Messages search-box bug (unwired onChange in Messages.jsx)

Day 2  Reproduce and fix the profile-update role-routing bug; regression test both fixes across all 5 roles

Day 3–4  Email: audit trigger coverage against real product actions; implement top 2–3 missing triggers; smoke test

Day 5–6  Notifications: coverage audit; add matching in-app triggers for the same gaps; smoke test

Day 7  Buffer; support integrated regression pass

Track B — Payments, Dashboard

Day 1–2  Payment QA: test-mode checkout for all plans, webhook simulation (success / failure / renewal), coupon flow, admin refund flow, signature-verification check

Day 3  Resolve duplicate jobseeker dashboards — merge HomeJobseeker.jsx and jobseeker/Dashboard.jsx, or clearly split their purpose

Day 4–5  Add 1–2 priority analytics widgets: company Analytics trend chart, jobseeker application-status breakdown

Day 6  Loading-state and performance check on both dashboards

Day 7  Buffer; support integrated regression pass

Track C — Verification   ·

Day 1  Lock scope with stakeholder: confirm this window covers status-flow polish only, not a new document-upload workflow

Day 2–3  Consistent status badges across ManageCompanies.jsx, CollegeVerification.jsx, CollegeKycDetails.jsx; show rejection reason and a resubmission path to the submitting user

Day 4–5  Add a lightweight audit-trail log (who approved/rejected, when, why) to the existing approve/reject actions

Day 6–7  Test across company, college, and student ID verification paths

Day 8  Buffer; support integrated regression pass

Day 8, all tracks: joint regression QA across all 5 roles, plus a stakeholder walkthrough and sign-off. If 6 days is a hard ceiling: drop Track A's Notifications pass (fold the minimal fix into the Email pass) and Track C's audit-trail logging (defer both fully to Phase 2). That brings all three tracks to 5–6 days, at the cost of a thinner verification and notification result.